## Total LoE UCaaS
DEPLOYMENT OMNIVIEW
|  |  | MX L6 | CO L5 | IN L5 | MX L3 | CO L5 | MX L3 | CO L5 | US L5
|  |  | 605.5956 | 341.4 | 164.871 | 213.74 | 341.4 | 213.74 | 341.4 | 872.56
| Activity | Description | MS PM | SDM | SUS | SUS2 | SME | Desk | CSS | Portal | Total Days
| SOP/ Omniview Provisioning | Project manager Provisioning | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 12.5%
| SOP/ Omniview Provisioning | Omniview Analysis and Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 20.83%
| SOP/ Omniview Provisioning | Omniview Software Installation and setup | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 41.67%
| SOP/ Omniview Provisioning | Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| SOP/ Omniview Provisioning | Solution validation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 20.83%
|  |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 21 | 24 | Total Days
|  | Contingency | 1211.1912 | 341.4 | 0 | 0 | 0 | 0 | 0 | 18323.76 | 19876.3512 | Cost
|  | 30% | 2.6 | 1.3 | 0 | 0 | 0 | 0 | 0 | 27.3 | 31.2 | Total Days Contingency
|  |  | 1574.5485 | 443.82 | 0 | 0 | 0 | 0 | 0 | 23820.888 | 25839.2565 | Cost Contingency
Global PM/SDM | 12.5% |  | 8.333% | 4.167% | 0% | 0% | 0% | 0% | 0% | 87.5% | 50% | Margin
Global LAD | 12.5% | [9 empty] | 0 | Expenses
Global NAM | 87.5% | [9 empty] | 51678.513 | Price
[11 empty] | 4306.5427 | Monthly Price